## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
| TOTAL LOC |  | 1600 | Note: Total LOC should be >= 900 * Number of project members
Function Name | Feature | Complexity | LOC | Planned Code Iteration | Student No | In-charge Full Name | Actual Code Iteration | SRS Status | Design Status | Coding Status | Testing Status | % Completed | Completed in Iteration
Note List | Note | Simple | 100 | Iteration 1 | SE05203 | Lưu Bảo Anh | Iteration 1 | Done |  | Done | Completed | 100% | Iteration 1
Note Details | Note | Simple | 100 | Iteration 2 | SE05203 | Lưu Bảo Anh | Iteration 2 | Done |  | Done | Completed | 100% | Iteration 2
Add Note | Note | Simple | 100 | Iteration 2 | SE05203 | Lưu Bảo Anh | Iteration 2 | Done |  | Done | Completed | 100% | Iteration 2
Edit Note | Note | Simple | 100 | Iteration 3 | SE05203 | Lưu Bảo Anh | Iteration 3 | Done |  | Done | Completed | 100% | Iteration 3
Delete Note | Note | Simple | 100 | Iteration 4 | SE05203 | Lưu Bảo Anh | Iteration 4 | Done |  | Done | Completed | 100% | Iteration 4
Search Note | Note | Simple | 100 | Iteration 1 | SE05203 | Lưu Bảo Anh | Iteration 2 | Done |  | Done | Completed | 100% | Iteration 2
Quiz Setting | Quiz | Simple | 100 | Iteration 1 | SE05203 | Lưu Bảo Anh | Iteration 1 | Done |  | Done | Completed | 100% | Iteration 2
Quiz Play | Quiz | Medium | 200 | Iteration 1 | SE05203 | Lưu Bảo Anh | Iteration 1 | Done |  | Done | Completed | 100% | Iteration 2
Export Quiz to Note | Quiz | Simple | 100 | Iteration 3 | SE05203 | Lưu Bảo Anh | Iteration 2 | Done |  | Done | Completed | 100% | Iteration 3
Review Quiz | Quiz | Simple | 100 | Iteration 3 | SE05203 | Lưu Bảo Anh | Iteration 2 | Done |  | Done | Completed | 100% | Iteration 2
Statistics | Statistics | Medium | 200 | Iteration 4 | SE05203 | Lưu Bảo Anh | Iteration 4 | Done |  | Done | Completed | 100% | Iteration 4
Dictionary | Dictionary | Complex | 300 | Iteration 2 | SE05203 | Lưu Bảo Anh | Iteration 1 | Done |  | Done | Completed | 100% | Iteration 1